## Sheet1
RISK ID | RISK DESCRIPTION | STRIDE | AFFECTED COMPONENT | LIKELIHOOD (1- 5) | IMPACT (1- 5) | RISK SCORE (L*I) | RISK LEVEL | EXISTING CONTROLS | CONTROL TYPE | PROPOSED MITIGATION PLAN | GSP SERVICE / TOOL | RESIDUAL RISK
R001 | Unauthorized access due to excessive IAM privileges | Elevation of Privilege | IAM / Service Accounts | 4 | 5 | 20 | High | Default IAM roles | Preventive, Detective, Corrective | Preventive: Enforce least-privilege IAM roles using IAM Recommender. Detective: Enable Cloud Audit Logs and SCC alerts for policy changes. Corrective: Revoke excessive roles immediately and rollback IAM policy. | Cloud IAM | Medium
R002 | Attacker exploits web application vulnerabilities to inject malicious SQL queries into Cloud SQL database | Tampering | Cloud SQL | 4 | 5 | 20 | High | Private subnet and TLS encryption | Preventive, Detective, Corrective | Preventive: Use parameterized queries and WAF SQLi rules. Detective: Monitor Cloud SQL Insights and audit logs for suspicious queries. Corrective: Restore DB from backup or PITR and patch application code. | Cloud Armor WAF, Cloud SQL IAM | Medium
R003 | Sensitive data in Cloud Storage buckets leaked | Information disclosure | Cloud Storage | 4 | 4 | 16 | High | Bucket-level IAM | Preventive, Detective, Corrective | Preventive: Enforce bucket-level access policies and block public access at org level. Detective: Enable SCC to flag public buckets and monitor access logs. Corrective: Remove public ACLs and rotate compromised data. | Cloud Storage IAM, DLP API | Low
R004 | Distributed denial of service (DDoS) attack floods Compute Engine instances, making website unavailable | Denial of service | Compute Engine | 4 | 4 | 16 | High | Cloud Armor | Preventive, Detective, Corrective | Preventive: Apply Cloud Armor rate-limiting and adaptive protection. Detective: Configure Cloud Monitoring alerts for abnormal traffic. Corrective: Scale MIG, block malicious IPs, and enable auto-healing. | Cloud Armor, Load Balancer | Low
R005 | Compromise of service account keys used by app tier | Spoofing | App tier(Cloud Functions, GCE) | 3 | 5 | 15 | High | IAM service accounts with limited roles. | Preventive, Detective, Corrective | Preventive: Enforce Workload Identity Federation and disable long-lived keys. Detective: Configure alerts on abnormal SA key usage in Cloud Logging. Corrective: Revoke compromised keys, rotate credentials, and redeploy workloads. | Cloud IAM, Workload Identity Federation | Medium
R006 | Missing or short retention of access logs. | Repudiation | All tiers(LB,App,DB) | 3 | 3 | 9 | Medium | Cloud Audit logs enabled by default | Preventive, Detective, Corrective | Preventive: Apply least-privilege IAM and restrict Owner/Editor roles. Detective: Enable SCC and Cloud Logging alerts for IAM role changes. Corrective: Revoke elevated permissions, rollback IAM changes, and enforce approvals. | Security Command Center | Low
R007 | Unencrypted database connections allow interception of sensitive data in transit | Information disclosure | Cloud SQL, Application Teir | 3 | 4 | 12 | High | Private network and connectivity | Preventive, Detective, Corrective | Preventive: Enforce 'Public Access Prohibited' on Cloud Storage at org level. Detective: Enable SCC and Monitoring to detect misconfigured buckets. Corrective: Remove public ACLs, re-encrypt sensitive files, rotate leaked data. | Cloud SQL, SSL/TLS | Low
R008 | Malicious file upload throuhg API leads to remote code execution | Elevation of Privilege | Cloud Functions, Compute Engine | 3 | 4 | 12 | High | Default file type validation | Preventive, Detective, Corrective | Preventive: Deploy Cloud SQL in HA mode and configure quotas. Detective: Enable Cloud Monitoring alerts for CPU, connections, and storage. Corrective: Failover to replica, restore from backup, and resize resources as needed. | Cloud Functions, Cloud Storage | Medium
R009 | Lack of database audit logs enables untraceable data manipulation | Repudiation | Cloud SQL | 3 | 3 | 9 | Medium | Default database logs | Preventive, Detective, Corrective | Enable Cloud SQL audit logging, set up aleerts for suspicious activities | Cloud SQL, Cloud Logging | Low
R010 | Cross-tier lateral movement through misconfigure firewall rules | Elevation of Privilege | VPC Network, Firewall | 3 | 4 | 12 | High | Default VPC Fireewall rules | Preventive, Detective, Corrective | Implement network segm entation with strict firewall rules, use service tags instead of IP ranges | VPC Firewall Rules, Network Tags | Medium
R011 | Unpatched software vulnerabilities in Compute Engine OS | Tampering | Compute Engine | 4 | 4 | 16 | High | Default OS images | Preventive, Detective, Corrective | Implement automated patch management, use shielded VMs, regular vulnerability scanning | OS Patch Management, Security Command Center | Medium
R012 | Weak passwords for database users allowing brute force attacks | Spoofing | Cloud SQL | 4 | 4 | 16 | High | Default authentication | Preventive, Detective, Corrective | Enforce strong password policy, use Cloud SQL IAM database authentication | Cloud SQL IAM Auth, Password Policy | Medium
R9 | Delayed patching on critical servers | Tampering | Compute Engine / VM Instances | 4 | 5 | 20 | High | Manual patching every quarter | Preventive | Implement automated patch management and regular compliance checks | OS Patch Management | Medium
R10 | Lack of multi-factor authentication (MFA) enforcement | Elevation of Privilege | IAM / User Accounts | 5 | 5 | 25 | Critical | Password-only authentication in place | Detective | Mandate MFA across all admin and service accounts | Google Identity Platform | Low
R11 | Misconfigured firewall rules allowing broad ingress traffic | Spoofing / Tampering | VPC Network | 4 | 5 | 20 | High | Default allow rules applied to 0.0.0.0/0 | Preventive | Restrict ingress rules to specific IP ranges and conduct quarterly firewall audits | VPC Firewall Rules | Medium
R12 | Lack of Cloud Storage object versioning and retention policy | Information Disclosure | Cloud Storage | 3 | 4 | 12 | Medium | No object versioning enabled | Corrective | Enable object versioning and lifecycle management to prevent accidental deletions | Cloud Storage Lifecycle | Low
R13 | Inactive service accounts not disabled | Elevation of Privilege | IAM | 4 | 4 | 16 | High | No automated process for service account lifecycle | Preventive | Implement automatic service account disablement for inactivity >90 days | IAM Policy + Security Command Center | Low
R14 | Missing security baseline compliance (CIS/GCP) | Information Disclosure | Organization Policy | 3 | 5 | 15 | High | Partial compliance to CIS Level 1 | Detective | Deploy Security Command Center compliance scanner and remediate findings monthly | Security Command Center | Medium
R15 | Lack of backup verification testing | Denial of Service | Cloud SQL / VM | 3 | 5 | 15 | High | Backups configured but never validated | Corrective | Schedule monthly backup restoration validation tests and maintain audit logs | Cloud SQL Backups | Low